## BOP
Business Opportunity Program (BOP) Checklist
Region / Group / Agency
Date
Location/Venue
Pre- BOP | Timeline | PIC | √ | BOP | PIC | √ | Post - BOP | Timeline | PIC | √
Venue logistics 1. Booking 2. Invoices and deposits (if any) 3. Reccee | T - 30 days |  |  | AV system 1. Sound system 2. Music and slide control |  |  | Compilation of guest list | T + 2 days
Source BOP speakers | T - 30 days |  |  | Registration - attendence, folder and stationeries |  |  | Commitment for examination forms | T + 1 day
Speakers slides preparation | T - 10 days |  |  | Emcee |  |  | Examination tutorials
Materials and handout Folders Registration forms Games | T - 7 days |  |  | Speaker liason Speaker 1 Speaker 2 Speaker 3 |  |  | Prepare final payment (if any) | T + 7 days
Promoting BOP # By emails, flyers, WhatsApp, invitation cards, phone calls, etc. | T - 30 days |  |  | Set up of venue 1. Buntings 2. Hall arrangements 3. Foyer arrangements 4. Meals arrangements |  |  | Post - Mortem for improvement updates | T + 2 days
Confirmation of No of Pax | T-7 days |  |  | Photographer |  |  | Tracking for 3 months | T + 3 mth
Examination and tutorial arrangements | T - 7 days
Transportation logistics | T - 10 days
To complete the tick box for weekly updates
In Progress
Completed
Not Started